## Slide 1
Projektiliiketoiminnan tutkimustuloksilla onnistumiseen Karlos Artto
Aalto-yliopisto
PSK:n kevätseminaari 2013
Pörssitalo, Fabianinkatu 14, Helsinki
18.4.2013
Project Business research group at Aalto University, Finland
http://pbgroup.aalto.fi/en/

## Slide 2: Projektiliiketoiminnan tutkimustuloksilla onnistumiseen
Menestys (kriteerit)
Aika (pitkä aikajänne, systeemin elinkaari)
Kenen näkökulma?
Projekti usean yrityksen verkostona

## Slide 3: Cost estimate overruns in road and rail infrastructure projects
Flyvbjerg 2006
Type of project
No. of cases (N)
Average cost overrun %
Standard deviation %
Rail
58
44,7
38,4
Bridges & tunnels
33
33,8
62,4
Road
167
20,4
29,9

## Slide 4: Channel Tunnel & Copenhagen Metro Ex post evaluation
Channel Tunnel
  Actual costs = 2 x estimate
  Actual benefits = ½ x forecast
  Actual NPV = $ -17,8 billion
  Actual IRR = -14,45 %
  Conclusion: ”The Bristish economy would have been better off had the tunnel never been constructed” (R. Anguera, Transportation Research A40, 2006)
Copenhagen Metro
  Actual costs = 3 x estimate
  Actual patronage = 0,6 x forecast
Flyvbjerg 2006

## Slide 5: Cost risks & benefit risks
Costs:
  9 out of 10 projects have cost overruns
    Based on data from 20 nations on 5 continents
  Overrun is constant for the past 70 years -> estimates have not improved
Benefits:
  9 out of 10 rail projects have overestimated traffic
    Average rail passenger shortfall is 51,4%
  Traffic forecasts have not improved for 30 years
Flyvbjerg 2006

## Slide 6: Applicable capital expenditure optimism bias uplifts for 50% and 80% percentiles, constant prices
Motorway
Trunk roads
Local roads
Bicycle facilities
Pedestrian facilities
Park and ride
Bus lane schemes
Guided buses on wheels
Metro
Light rail
Guided buses on tracks
Conventional rail
High speed rail
Bridges
Tunnels
Stations
Terminal buildings
IT system development
Roads
Rail
Fixed links
Building projects
IT projects
Std civil eng.
Non-std civ. eng.
15 %
40 %
23 %
4 – 51 % *
10 – 200 % *
3 - 44 % *
6 – 66 % *
32 %
57 %
55 %
Types of projects
Category
50 % percentile
80 % percentile
Applicable optimism bias uplifts
* based on Mott MacDonald (2002)
Flyvbjerg 2006

## Slide 7: A firm’s view on project success
Time elapsed before measurement is possible
Level of hierarchy required to give commitment
Cooke-Davies, 2004
Project Management success –
Was the project done right?
Project success –
Was the right project done?
Consistent project success –
Were right projects done right, time after time?

## Slide 8: Project success criteria in time
Time
Uncertainty
Time
Scope
Cost
Impact
Relevance
Goal achievement
Economic effects
Needs satisfaction
Societal effects
Samset, 2003

## Slide 9: Factors and Criteria comparison
How to achieve success?
What success is?
Factors
Criteria
0
Project
Post-project
LINK
Time

## Slide 10: Specific Success Measures
Impact on
Customer
Impact on
Team
Business & Direct Success
Project Success
Meeting schedule
Meeting budget
Changes
Yield
Other efficiencies
Meeting requirements and specifications
Benefit to customer
Extent of use
Customer satisfaction & loyalty
Brand name recognition
Team satisfaction
Team morale
Skill development
Team member growth
Team members’ retention
No burnout
Sales
Profits
Market share
ROI, ROE
Cash flow
Service quality
Cycle-time
Organizational measures
Regulations approval
New technology
New market
New product line
New core competencies
New organizational capabilities
Preparing for Future
Efficiency
Adopted from: Shenhar & Dvir, 2007

## Slide 11: Evaluating the effects of a project
Source: Samset, 2003
Inputs / resources
Operational objectives
Tactical objectives
Strategic objectives
Needs / Priorities
Internal efficiency
External effectiveness
Impact of effects
Relevance of effects
Sustainability of effects
Project
Process

## Slide 12: Modelling effects
Outputs
Mechanisms of effect
Effects
Web-based
Customer
information
Web-based
service
information
Web-based
transactions
Fever
queries
Less
Dependence on
staff
24x7
availability
Greater awareness
Better
Take-up service
Less advertising in
papers
One-stop information
collection
Standardization of
forms
Faster processing
More time for
Other tasks
Reduced
expenditures
Customer
satisfaction
Increased
effectiveness
Better market
image
Better quality
ïnformation
Fever
Phone calls,
Less mail
modified from: OGC, 2003

## Slide 13: From an individual projects towards the businesses among firms: Two interrelated layers: permanent business network and temporary project networks
Active project
Active project
No project
Active project
Active project
No project
Project
networks
Business
network
of individual
projects
modified from Eloranta 2007 (= Kirsi Aaltonen, 2007)
& Artto, Eloranta, & Kujala, 2008
(of firms or of organizations)

## Slide 14: Subcontractors’ business relationships as risk sources in project networks
Client
Competitor
Non-
business actor
Contractor
Sub-
contractor
Sub-
contractor
Artto, Eloranta, Kujala 2008

## Slide 15: Building market position: case Metso in Russian oil and gas markets
Ahola T., Kujala J., Aaltonen K., Laaksonen T. (2013). Constructing the market position of a project-based firm. International Journal of Project Management, 31(3):355-365.
In order to be successful project-based firms need to create
  Core technologies, competences and delivery capability (functional positioning)
  Relationships with key business and non-business related actors (relational positioning)
  These two interrelated concepts form market position of a project-based firm.

## Slide 16: Challenge for Metso Automation in 1990’s
In late 1990’s Metso Automation had very few deliveries for Oil and Gas business in Russia
It was not well known and considered as capable supplier in the market segment
Project product (=delivery of complete system to customer) had not been modified to meet specific requirements of this market segment
The market potential was very large and a few big customers dominated the market

## Slide 17
Структура системы metsoDNA

## Slide 18: Case Surgutneftegaz (SNG)
1 Identified as potential customer in May 1996
2 General marketing
3 Project selection (3 compressor stations) Q3/98
4 Solution outlines, discussions Q4/98-Q1/99
5 Quotation Q2/99
6 Sales process and negotiation process
7 Tender won and contract signed in July 1999
1996 1997 1998 1999
1
2
3
x
4
5,6, 7
x
After these 3 systems SNG has ordered more than 50 deliveries from Metso Automation

## Slide 19: ОАО «Сургутнефтегаз» 2000–2010
    Западня Сибирь:
    Компрессорная станция 3/1 и 3/2 Лянторского м/р
    ГТЭС Тяньского м/р
    Компрессорная станция 42 Федоровского м/р
    Битумный завод (Установка получения битума)
    Компрессорная станция 1 Лянторского м/р
    Компрессорная станция 2 Лянторского м/р
    Компрессорная станция 7/2 Федоровского м/р
    Компрессорная станция 44 Федоровского м/р
    ГТЭС Биттемского м/р
    ГТЭС Русскинского м/р
    ГТЭС на ДНС-1 Лукъявинского м/р
    ГТЭС на КНС-11 Лянторского м/р
    ГТЭС на КНС-17 Лянторского м/р
    Компрессорная станция 41 Федоровского м/р
    ГТЭС на ДНС-12 Конитлорского м/р
    ГТЭС на ДНС-7 Юкьяунского м/р
    ГТЭС на ДНС-3 Мурьяунского м/р
    ГТЭС Западно-Камынского м/р
    Компрессорная станция 7/1 Федоровского м/р
    Компрессорная станция 1 Лянторского м/р – расширение
    ГТЭС Тромъеганского м/р
    ГТЭС Северо-Лабатьюганского м/р
Сургут
    ГТЭС Западно-Чигоринского м/р
    ГТЭС Верхне-Надымского м/р
    УКПГ (установка компремирования и подготовки газа) Рогожинского м/р
    Компрессорная станция Айпимского м/р
    Битумный завод Расширение
    Компрессорная станция 7/2 Федоровского м/р 2010
    ГТЭС-2 Рогожинского м/р
    Компрессорная станция 3/1 и 3/2 Лянторского м/р Расширение
    ГТЭС Тяньского м/р Расширение (2011)
    ГТЭС-2 Северо-Лабатьюганского м/р (2011)
    Якутия:
    Компрессорная станция Талаканского м/р
    ГТЭС Талаканского м/р
    ГТЭС-2 Талаканского м/р
    Установка получения битума
    Резервуарный парк и станция перекачки топлива
    ГТЭС - газо-турбинная элкетростанция

## Slide 20: How to use project deliveries to develop stronger market position?
Relational position at end of 1999
Relational position at end of 2005

## Slide 21: Processual model of project marketing supported by repetitive project deliveries

## Slide 22
Project success criteria framework (by Artto & Ahola, under development)
Artto & Ahola, 2013 (Draft)
The project at hand: Time/Cost/ Scope
The time dimension: Long-term future considerations
The supply/value chain dimension: Your upstream subcontractor, and Your downstream customer

## Slide 23
 | Subcontractor | Focal organization | Customer
Efficiency | Time: The strict schedule requirements were transferred to the subcontractors | Time: The contract included high delay penalties. Therefore, some equipment deliveries were shipped to the site too early without appropriate testing procedures. This caused problems on the site and some of the deliveries were shipped back to the workshop in another country. Finally, the project was executed in time. Cost: Cost overruns occurred due to problems with installation and the returned deliveries. Scope: The delivered system works with full capacity and even above its defined performance requirements | Time: The customer changed the intended time-table many times during the project. Safety: Safety requirements in the target country are strict and therefore the customer hired an external consultant to supervise security measures on the site.
Short-term impact | Learning: One subcontractor delivered a unique subsystem with unique technology in the global market. This project opened new business opportunities for the subcontractor. | Profitability: The project was not a success in terms of profitability, but major losses were avoided Learning: Valuable lessons from managing work safety requirements and procurement. | Meeting the requirements of local and institutional stakeholders: The presence of the local trade-union was strong – they set strict definitions for safety reporting and denied executing two work shifts simultaneously. This caused challenges to the time-table.
Long-term impact | Partnerships: The project introduced a new technological application area for a trusted subcontractor, which will be utilized in future projects | New technology: The project was first of its kind for constructing a system for treating this raw material with this particular process technology; Strategic reference/new market: The system acts as a strategic reference for further project deliveries; A similar system is already being built for another customer Organizational renewal: Experience from delivering novel technologies with fixed price and performance guarantees | Brand and reputation: A safe and working system with high performance is of particular value to the customer.

## Slide 24: ”Business in Built Environment BBE”: The complex system integrates the business models of multiple stakeholders
System
Energy company
System expert
Aalto-university, researchers
Energy – effeciency expert
User - operator
Final customer
Contractor, system builder
Service provider
Customer
Financier
Shareholder

## Slide 25: ”Business in Built Environment BBE”: The life cycle of a complex system
System
System
System
Initiation and creation
Development
Operations

## Slide 26: Project Business research group (PB)
Aalto University
School of Science
P.O. Box 15500
FI-00076 Aalto
Finland
email: firstname.lastname@aalto.fi
www: http://pbgroup.aalto.fi/en/
http://pbgroup.aalto.fi/en/

## Slide 27: Spare slides

## Slide 28: The importance of procurement criteria: the customer vs supplier view
The procuring customer’s view | The suppliers’ view
Capability to keep the schedule (6,5) | Price of products, services and solutions (6,5)
Quality of products, services and solutions (6,5) | Capability to keep the schedule (5,0)
Price of products, services and solutions (6,4) | Project management capability (5,0)
Project management capability (6,3) | Experiences from previous projects (4,9)
Capability to manage own sub-contractors /integration capability (6,3) | Available capacity (4,7)
Available capacity (6,0) | Capability to manage own subcontractors /integration capability (4,4)
Economic wealthiness of the contractor (5,6) | Quality of products, services and solutions (4,2)
Experiences from previous projects (5,5) | Economic wealthiness of the contractor (3,6)
1.
2.
3.
4.
6.
5.
7.
9.
1.
2.
3.
5.
9.
12.
14.
15.
Ahola & Westerholm, 2008

## Slide 29: A simplified/adjusted business model characterization
Offering and/or value proposition
Relationship
Network of partners and/or suppliers
Core capabilities
Customer
Profit-making logic
By Karlos Artto, 2013

## Slide 30
Project success criteria framework (by Artto & Ahola, under development)
Artto & Ahola, 2013 (Draft)

## Slide 31
Project success criteria framework in a project supply chain of multiple firms
(by Artto & Ahola, under development)
Artto & Ahola, 2013 (Draft)
Subcontractor
(or supplier)
Contractor
(or systems integrator)
Customer
(e.g. owner-operator)
X
X
X
X
The mark
anticipated initial locus of
success criteria
indicates the

## Slide 32: Challenges with risk management in firms
Risk identification and analysis is conducted only once properly
Risk management activities are done only because company rules say so
The applications of the generic risk management process are exhaustive
Risk check lists kill creativity
Content of risk check lists
IT-systems or tools are not too helpful, as the actual effect comes from interaction among individuals
Lack of facilitators that would serve as talk show hosts
Risk management gets isolated to become only the responsibility of the project manager or a risk analyst
Learning concerning risks occurs through on ex-post analyses and is based on documenting risks

## Slide 33
Identification
Estimation
Response planning
It tool 1
It tool 2
1
PROJECT
RM
PM
2
3
”Risks must be managed, so just do it”.
4
Executive
Project manager
Service manager
Sales manager
5
Disintegration
Notes: 33

## Slide 34: ”Project business” definition
“Project business is the part of business that relates directly or indirectly to projects, with the purpose of achieving objectives of a firm or several firms.”
( from: Artto & Wikström, 2005, IJPM article on: “What is project business?” )

## Slide 35: Project business framework: literature sources that elaborate the framework
Article:
  Artto K., Kujala J. (2008). Project business as a research field, International Journal of Managing Projects in Business, 1(4):469-497
Book chapter:
  Artto K., Davies A., Kujala J., Prencipe A., (2010). The project business: analytical framework and research opportunities. Chapter 5 (pages 133-153) in: Morris P. W. G., Pinto J., Söderlund J. (eds.), Oxford Handbook of Project Management, Oxford University Press, Oxford, UK

## Slide 36: Project business framework: four distinctive management areas
Artto & Kujala (2008)
Artto, Davies, Kujala, & Prencipe, 2011
See a brief explanation of this framework from the “Foreword to the 1st English language edition (2011) of ‘Project business’ book, downloadable from http://pbgroup.aalto.fi/en/
One project
Many projects
One firm
Many firms
1. Management of a project
3. Management of a project network
2. Management of a project-based firm
4. Management of a business network

## Slide 37: Project business framework: four distinctive management areas and their interfaces
One project
Many projects
One firm
Many firms
1. Management of a project
3. Management of a project network
2. Management of a project-based firm
4. Management of a business network
Interface 1-3
Interface 1-2
Interface 2-4
Interface 3-4
Artto & Kujala (2008)

## Slide 38: Characterizing the project business research field: distinctive contents of the four major areas
1. Management of a project
3. Management of a project network
2. Management of a project-based firm
4. Management of a business network
Management object: A project.
Measure of success: Meeting of predefined project goals.
Significant contingency factors: Project uniqueness, novelty, technology, complexity, pace.
Management object: A firm.
Measure of success: Achievement of short-term and long-term business objectives of the firm.
Significant contingency factors: Discontinuity, interdependence between projects, market and technological uncertainty.
Management object: A project as a multi-firm network.
Measure of success: Meeting of project’s goals with simultaneous achievement of expectations and business objectives of the firms participating in the project.
Significant contingency factors: Participating firms, asymmetry of their objectives, interests and identities.
Management object: A network of firms and their relationships.
Measure of success: Competitiveness and capability of individual firms and networks to create and implement new projects.
Significant contingency factors: Norms and culture, institutional issues, governance schemes, relationship between firms, role stability.
Artto & Kujala (2008)

## Slide 39: Project business framework with specific research areas and themes
1. Management of a project
3. Management of a project network
2. Management of a project-based firm
4. Management of a business network
management of risk and uncertainty
contingency theory view and systems view on projects
project strategy
inside-out management of project’s interface to its context
theory of project-based firm and the firm’s business model
learning, capabilities and competencies
selling and delivering projects
procurement and supplier network management
the role and management of products in the business of a
project-based firm
the role of services in the business of a project-based firm
portfolio and program management
resource management in a project-based firm
large projects research
project as network of firms
project as multi-organization enterprise
dynamism in project network
learning within the project network
stakeholder management
systems integration
project delivery chain and supply chain management
within a project
governance in project network
interplay between temporary project networks and
the permanent business network
measurement of performance in business network
analysis of networked business environment and
design of the firm’s strategy
ever-changing roles of the network’s players
multiple conflicting interests and fragmented entities
even within one single firm
embedded innovation in business activities in the network
moving base in the value stream
Interface 1-2
Interface 3-4
Interface 1-3
Interface 2-4
Artto & Kujala (2008)

## Slide 40: The main managerial challenges in the four areas of the project business
1. Management of a project
3. Management of a project network
2. Management of a project-based firm
4. Management of a business network
Unit of analysis: A project as a business entity.
Managerial challenge: … to manage a single project effectively in its environment by taking into account that the project is a purposeful business entity and the management of its inherent business content can be compared to the management of a firm’s business.
Unit of analysis: A firm or a portfolio of projects.
Managerial challenge: … to manage a firm and its multiple projects as a whole, by ensuring that projects support the strategy and business objectives of the firm, by simultaneously allocating the firm’s scarce resources to projects.
Unit of analysis: A project as a multi-firm network.
Managerial challenge: … to manage a project as a multi-firm enterprise through managing multiple firms participating to the project, by creating a contractual or an organizational arrangement that enhances goal alignment and coordination across multiple firms.
Unit of analysis: A network of firms and their relationships.
Managerial challenge: … to manage a network of actors and their relationships in an open and competitive business marketplace where the firms may or may not engage in joint projects with other firms. From a single firm’s or project’s viewpoint, maintaining efficiency and innovativeness in the network is central, and is affected by how the firms and projects decide to position themselves in the value network of all business players and non-business actors.
Artto, Davies, Kujala, & Prencipe (2010)

## Slide 41: The free-of-charge ”Project business” book -> download
The ” book can be downloaded free-of-charge from the Project Business research group’s webpage:
http://pbgroup.aalto.fi/en/the_book_and_the_glossary/
The bibliographic data of the book:
in English:
  ”Artto K., Martinsuo M., Kujala J., 2011. Project business. Helsinki, Finland, http://pbgroup.aalto.fi/en/ , (ISBN 978-952-92-8535-8) “
in Finnish:
  ”Artto K., Martinsuo M., Kujala J., 2006. Projektiliiketoiminta. WSOY, Helsinki, http://pbgroup.aalto.fi/en/ , (ISBN 978-952-92-8534-1)“